Document 5 of 6

Build Plan & Acceptance

Phasing, Milestones & Definition of Done

How to sequence the build and verify each part is correct

BioCore Platform — Build Documentation Package

Stack: FastAPI · Next.js · PostgreSQL · Milvus · MinIO · Redis

Contents

Part 1 Build Sequence

# 1. Build sequence

Build in this order. Each phase produces something testable and depends only on earlier phases. Do not start a later phase before its predecessor passes acceptance.

## 1.1 Phase 0 — Foundation (weeks 1–2)

- Set up the repo, CI/CD, Docker Compose with all containers running.

- Stand up PostgreSQL with the core tables (tenants, users, roles, consent, audit).

- Deploy ZepIris and confirm enroll + search work with a test image.

- Build the API gateway, session auth, and CSRF.

Phase 0 done when A developer can register a tenant, create an admin, log in, and the session cookie works. ZepIris returns a vector for a test face and a match on a second image of the same face.

## 1.2 Phase 1 — Core attendance MVP (weeks 3–6)

- Self-registration flow (register → OTP → consent → face enroll).

- Kiosk check-in screen with face search + toggle logic.

- Admin dashboard: overview, attendance log, users list.

- Device registration and pairing.

Phase 1 done when A person can self-register on a browser and then check in/out at a kiosk. The admin sees the event live on the dashboard and in the attendance log. This is a working product for the Office, Gym, and basic School/Factory verticals.

## 1.3 Phase 2 — Access, zones, badges, DPDP (weeks 7–10)

- Zones, badges, and access-control decisions with door webhooks.

- Admin-assisted enrollment (unlocks Hospital, Government, Religious).

- Full DPDP suite: data export, erasure cascade, consent revoke, audit viewer.

- Blacklist + real-time alerts; visitor temp-enrollment.

## 1.4 Phase 3 — Modules (weeks 11–16)

- Wage calculation, break tracking, GPS check-in, emergency headcount.

- Class timetable + guardian pickup (School).

- Membership billing (Gym), donations (Religious), event bulk import + badges.

- ERP webhooks and reporting/export.

## 1.5 Phase 4 — Advanced ML (weeks 17–20)

- PPE / safety-gear detection (needs a training dataset).

- Zone movement tracking for high-security sites.

Realistic team & timeline This is a 4–6 month build for a small team: 2 backend, 2 frontend, 1 ML, 1 designer, 1 QA. A solo freelancer would take much longer and should not attempt the DPDP and security parts without review. Treat the phases as fixed-scope milestones with payment tied to acceptance.

Part 2 Acceptance Criteria

# 2. Acceptance criteria

A feature is 'done' only when it meets its acceptance criteria. These are the contractual definition of done — tie milestone payments to them.

## 2.1 Self-registration

- A new user can register with a valid org code; an invalid code is rejected.

- Email OTP is required and expires after 10 minutes.

- Face enrollment is blocked until all four consent boxes are ticked.

- The raw image is deleted after the vector is generated (verify it is not in MinIO).

- A duplicate email returns a clear 409 error.

## 2.2 Kiosk check-in

- A registered face is matched in under 2 seconds and the event is recorded.

- Toggle logic correctly alternates check-in and check-out.

- An unregistered face shows 'not registered' and logs the no-match.

- A printed photo is rejected by spoof detection.

- A blacklisted face raises an immediate alert.

- The event appears on the admin dashboard live feed within 10 seconds.

## 2.3 Multi-tenancy

- A user in tenant A can never see or match against tenant B's data.

- Attempting a cross-tenant ID in any request returns 404, not another tenant's data.

- Row-Level Security blocks a leak even if app code forgets a filter (test this deliberately).

## 2.4 DPDP compliance

- No face can be enrolled without a consent record on file.

- Data export returns all of a user's data in a machine-readable format.

- Erasure deletes the vector (Milvus), image (MinIO), records (Postgres), and sessions (Redis), and each deletion is verified.

- An erasure certificate is generated with a reference ID.

- Every face search, enroll, and delete writes an audit log entry with a request ID.

- The audit log cannot be edited or deleted through the API.

## 2.5 Security

- All traffic is TLS 1.3; HTTP is refused.

- Session cookies are HttpOnly, Secure, SameSite=Strict.

- Mutations without a valid CSRF token are rejected.

- Admin login requires TOTP 2FA.

- A penetration test finds no critical or high vulnerabilities before go-live.

Part 3 Testing & Handover

# 3. Testing & handover

## 3.1 Required test coverage

| Test type | Covers | Minimum |
| --- | --- | --- |
| Unit tests | Business logic, toggle logic, wage calc | 80% of service code |
| Integration tests | API endpoints end-to-end | Every endpoint, happy + error paths |
| Isolation tests | Cross-tenant leak attempts | Every tenant-owned table |
| DPDP tests | Consent gate, erasure cascade | All criteria in 2.4 |
| Load test | Concurrent kiosk scans | Target peak × 2 |
| Security test | Pen test before go-live | Zero critical/high |

## 3.2 Handover checklist

The freelancer must deliver all of the following before final payment:

- Full source code in your repository, with README and setup instructions.

- Docker Compose / Kubernetes configs that bring the whole stack up with one command.

- Database migration scripts (reversible).

- All environment variables documented.

- Passing test suite with a coverage report.

- API documentation generated from code (OpenAPI/Swagger at /docs).

- A penetration test report with no critical/high issues.

- A short admin operations guide (start/stop, backup/restore, add a tenant).

- A recorded walkthrough of each acceptance criterion passing.

Protect yourself — contract advice Tie each milestone payment to its acceptance criteria, demonstrated live. Keep the code in YOUR repository from day one — not the freelancer's. Require the security/DPDP work to be independently reviewed; biometric data carries real legal liability under DPDP. This is general guidance, not legal advice — have a lawyer review the build contract.

End of Build Plan & Acceptance